Test Plan

Police Clearance Services (PCS) Portal - Maharashtra Police

Document Version: 1.0
Prepared By: QA Manager
Date: January 10, 2026
Project: Police Clearance Services Online Application System

1. Executive Summary

This test plan outlines the quality assurance strategy for the Police Clearance Services portal (https://pcs.mahaonline.gov.in), which enables citizens to apply for police clearance certificates online through a six-step process including registration, application, payment, and dual verification by local police stations and CFC.

2. Scope

2.1 In Scope

Functional Testing:

- User Registration module with email/mobile verification

- Login/Logout functionality with session management

- Forgot Password and Password Reset workflows

- Citizen Verification module for unverified users

- Application Form submission (Step 3) with all mandatory/optional fields

- Fee Payment integration and transaction processing

- CAPTCHA validation mechanism (BotDetect)

- Document upload functionality (photos, identity proofs, address proofs)

- Application status tracking

- Digital signature validation process

- CSC/VLE Center list and search functionality

- User manual and instruction PDF downloads

- Multi-language support (if applicable)

- Email/SMS notifications at each step

- Admin/Police Station verification workflows

- CFC verification workflows

- Certificate generation and download

Non-Functional Testing:

- Performance testing (load, stress, volume testing)

- Security testing (authentication, authorization, data encryption, SQL injection, XSS)

- Usability testing (UI/UX, accessibility compliance)

- Compatibility testing (browsers, devices, operating systems)

- Database integrity testing

- API testing for payment gateway integration

- Disaster recovery and backup procedures

Integration Testing:

- Payment gateway integration (multiple payment modes)

- SMS gateway integration

- Email server integration

- Digital signature verification system

- Government database integration (if any)

2.2 Out of Scope

- Testing of third-party payment gateway internal systems

- Testing of BotDetect CAPTCHA library internals

- Testing of MahaIT infrastructure beyond application scope

- Migration testing from legacy systems (if not planned)

- Testing of police station backend systems

- Physical document verification by police personnel

- Background verification processes conducted offline

- Testing of external systems (CCTNS, IVFRT databases)

- Performance of end-user internet connectivity

- Mobile application testing (if separate native apps exist)

3. Test Approach

3.1 Testing Strategy

Phase 1: Requirements Analysis (Week 1)

- Review functional specifications and user manuals

- Identify test scenarios from user journeys

- Create traceability matrix

Phase 2: Test Planning and Design (Week 1-2)

- Develop test cases for all modules

- Prepare test data sets

- Define entry/exit criteria

- Set up test environment requirements

Phase 3: Test Execution (Week 3-6)

- Smoke testing for build validation

- Functional testing across all modules

- Integration testing with payment gateways

- Regression testing for bug fixes

- Security and performance testing

- UAT support

Phase 4: Defect Management and Closure (Week 7-8)

- Defect retesting and closure

- Final regression cycle

- Test summary report preparation

3.2 Testing Types

| Testing Type | Priority | Allocation |
| --- | --- | --- |
| Functional Testing | High | 40% |
| Integration Testing | High | 20% |
| Security Testing | Critical | 15% |
| Performance Testing | High | 10% |
| Usability Testing | Medium | 5% |
| Regression Testing | High | 10% |

3.3 Test Levels

- Unit Testing: Performed by developers

- Integration Testing: QA team with development support

- System Testing: QA team

- User Acceptance Testing: Police department stakeholders and sample citizens

4. Test Environment

4.1 Environment Setup

Development Environment:

- Purpose: Initial testing by developers

- Database: Dev DB with synthetic data

- URL: dev-pcs.mahaonline.gov.in

QA/Testing Environment:

- Purpose: Complete test cycle execution

- Database: QA DB mirroring production schema

- URL: test-pcs.mahaonline.gov.in

- Payment: Test payment gateway integration

Staging/Pre-Production Environment:

- Purpose: UAT and final validation

- Database: Clone of production with masked data

- URL: uat-pcs.mahaonline.gov.in

- Payment: Staging payment gateway

Production Environment:

- Purpose: Live system

- URL: pcs.mahaonline.gov.in

- Monitoring: Production smoke tests post-deployment

4.2 Browser and Device Matrix

Desktop Browsers:

- Chrome (latest 2 versions)

- Firefox (latest 2 versions)

- Microsoft Edge (latest 2 versions)

- Safari (latest version for Mac)

Mobile Browsers:

- Chrome Mobile (Android)

- Safari Mobile (iOS)

- Samsung Internet Browser

Operating Systems:

- Windows 10/11

- macOS (latest 2 versions)

- Android 10+ (mobile responsive)

- iOS 14+ (mobile responsive)

Screen Resolutions:

- Desktop: 1920x1080, 1366x768, 1280x1024

- Tablet: 1024x768, 768x1024

- Mobile: 375x667, 414x896, 360x640

5. Timeline and Milestones

| Phase | Duration | Start Date | End Date | Deliverables |
| --- | --- | --- | --- | --- |
| Test Planning | 1 week | Week 1 | Week 1 | Test Plan, Test Strategy |
| Test Design | 1 week | Week 1 | Week 2 | Test Cases, Test Data |
| Environment Setup | 3 days | Week 2 | Week 2 | Test Environments Ready |
| Smoke Testing | 2 days | Week 3 | Week 3 | Smoke Test Results |
| Functional Testing | 2 weeks | Week 3 | Week 5 | Test Execution Reports |
| Integration Testing | 1 week | Week 4 | Week 5 | Integration Test Report |
| Security Testing | 1 week | Week 5 | Week 6 | Security Assessment Report |
| Performance Testing | 1 week | Week 5 | Week 6 | Performance Test Report |
| Regression Testing | 1 week | Week 6 | Week 7 | Regression Test Results |
| UAT Support | 1 week | Week 7 | Week 8 | UAT Sign-off |
| Test Closure | 3 days | Week 8 | Week 8 | Test Summary Report |

Total Duration: 8 weeks

Key Milestones:

- M1: Test Plan Approval (End of Week 1)

- M2: Test Case Review Complete (End of Week 2)

- M3: Functional Testing Complete (End of Week 5)

- M4: Non-Functional Testing Complete (End of Week 6)

- M5: UAT Sign-off (End of Week 8)

- M6: Production Deployment (Week 9)

6. Risks and Mitigation

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Payment gateway integration delays | High | Medium | Early engagement with payment partner, mock server for testing, parallel track for gateway testing |
| Incomplete or ambiguous requirements | High | Medium | Regular stakeholder meetings, requirement clarification sessions, early prototype reviews |
| Test environment unavailable/unstable | High | Medium | Dedicated DevOps support, environment monitoring, backup environment provisioning |
| Insufficient test data | Medium | Medium | Automated test data generation scripts, data masking tools for production data |
| Resource availability constraints | High | Low | Cross-training team members, buffer in timeline, backup resource pool |
| Security vulnerabilities discovered late | Critical | Low | Security testing in early phases, code review, penetration testing by third party |
| Browser compatibility issues | Medium | Medium | Early compatibility testing, BrowserStack/Sauce Labs tools, progressive enhancement approach |
| Performance degradation under load | High | Medium | Early performance baseline, continuous monitoring, scalability planning with infra team |
| Third-party service downtime (SMS/Email) | Medium | Low | Queue-based retry mechanisms, fallback notification methods, service level agreements |
| Digital signature validation failures | High | Low | Thorough integration testing, vendor support engagement, fallback manual verification process |
| CAPTCHA accessibility issues | Medium | Medium | Accessibility audit, alternative CAPTCHA options, audio CAPTCHA testing |
| Data privacy compliance issues | Critical | Low | Privacy impact assessment, legal review, compliance with IT Act and data protection regulations |

7. Dependencies

7.1 Internal Dependencies

- Development Team: Timely delivery of builds, bug fixes, and API documentation

- Business Analysts: Requirements clarification and use case validation

- DevOps Team: Environment provisioning, deployment support, database setup

- Security Team: Security requirements, vulnerability assessment support

- Database Administrators: Database setup, data masking, backup/restore procedures

- Project Management: Resource allocation, stakeholder coordination, timeline management

7.2 External Dependencies

- Payment Gateway Provider: Test credentials, API documentation, support for integration issues

- SMS Gateway Provider: Test environment access, message delivery monitoring

- Email Service Provider: SMTP configuration, deliverability testing

- BotDetect CAPTCHA: License validation, integration support

- MahaIT Infrastructure: Server availability, network connectivity, SSL certificates

- Police Department Stakeholders: UAT participation, verification workflow validation

- Digital Signature Service Provider: Integration specifications, validation API access

- Government Compliance Bodies: Data privacy guidelines, security standards

7.3 Hardware/Software Dependencies

- Test automation tools (Selenium, JMeter, Postman)

- Browser testing tools (BrowserStack/Sauce Labs)

- Performance monitoring tools (New Relic, Dynatrace)

- Security scanning tools (OWASP ZAP, Burp Suite)

- Defect tracking system (Jira, Bugzilla)

- Test management tool (TestRail, Zephyr, qTest)

8. Entry and Exit Criteria

8.1 Entry Criteria

- Test plan approved by stakeholders

- Test environment setup completed and validated

- Test cases reviewed and approved

- Test data prepared and validated

- Application build deployed in test environment

- Smoke test passed

- Defect tracking system configured

- Required access permissions granted to QA team

- Integration test accounts created (payment, SMS, email)

8.2 Exit Criteria

- 100% of planned test cases executed

- 95%+ test case pass rate achieved

- All critical and high priority defects resolved and verified

- No open blocker defects

- Regression testing completed successfully

- Performance benchmarks met (response time, concurrent users)

- Security vulnerabilities addressed (no critical/high severity issues)

- UAT sign-off received from stakeholders

- Test summary report completed and approved

- Production deployment checklist validated

- Knowledge transfer completed

9. Defect Management

9.1 Defect Severity Classification

- Critical: System crash, data loss, security breach, payment failure

- High: Major functionality broken, incorrect certificate generation, verification failure

- Medium: Minor functionality issues, UI problems, validation errors

- Low: Cosmetic issues, typos, minor UI enhancements

9.2 Defect Priority Classification

- P0: Fix immediately, blocks testing

- P1: Fix in current sprint

- P2: Fix in next sprint

- P3: Fix when time permits

9.3 Defect Workflow

- Defect logged in tracking system with reproduction steps

- Defect triaged by QA lead and assigned severity/priority

- Development team reviews and assigns to developer

- Developer fixes and updates status to "Fixed"

- QA retests and closes or reopens defect

- Weekly defect review meetings for aging issues

10. Test Deliverables

10.1 Before Testing

- Test Plan document

- Test Strategy document

- Test Cases and Test Scripts

- Test Data sets

- Traceability Matrix (Requirements to Test Cases)

10.2 During Testing

- Daily test execution status reports

- Weekly test progress reports

- Defect reports and metrics

- Test logs and screenshots

- Risk and issue logs

10.3 After Testing

- Test Summary Report

- Test Metrics Dashboard (test coverage, pass/fail rates, defect density)

- Defect Analysis Report

- Performance Test Results

- Security Assessment Report

- UAT Sign-off Document

- Lessons Learned Document

- Test Environment Handover Document

11. Roles and Responsibilities

| Role | Responsibility | Count |
| --- | --- | --- |
| QA Manager | Test planning, resource management, stakeholder communication, risk management | 1 |
| QA Lead | Test design, execution oversight, defect triage, reporting | 1 |
| Senior QA Engineers | Functional testing, integration testing, test automation | 2 |
| QA Engineers | Test case execution, defect logging, regression testing | 3 |
| Performance Tester | Performance and load testing, analysis | 1 |
| Security Tester | Security testing, vulnerability assessment | 1 |
| Automation Engineer | Test automation framework, script development | 1 |

Total Team Size: 10 resources

12. Test Metrics and Reporting

12.1 Key Metrics

- Test Coverage: (Test Cases Executed / Total Test Cases) × 100

- Test Execution Rate: Test cases executed per day

- Defect Detection Rate: Defects found per test case

- Defect Density: Defects per module/feature

- Defect Leakage: Production defects / Total defects

- Test Pass Rate: (Passed Tests / Total Tests) × 100

- Defect Resolution Time: Average time to fix defects

- Automation Coverage: (Automated Tests / Total Tests) × 100

12.2 Reporting Frequency

- Daily: Test execution status, blockers

- Weekly: Detailed progress report, defect summary, risk updates

- Milestone: Phase completion reports

- Final: Comprehensive test summary report

13. Assumptions

- Development team will provide builds with unit testing completed

- Test environment will be available 90%+ of the time

- Payment gateway test environment will be available as per schedule

- Stakeholders will be available for requirement clarifications within 24 hours

- UAT participants will be available during UAT phase

- Production-like data will be available for testing

- All third-party integrations will provide adequate testing support

- Security and performance requirements are documented

- Adequate licensing for testing tools is available

End of Test Plan